## Product Backlog
Product backlog
ID | Product backlog item | User stories | Priority | Story Points
User
1 | Create account | As a user I need to be able to create an account so I can log in to the system. | High | 3
2 | Change password | As a user I need to be able to change my credentials so I can keep my account secure | Low | 6
3 | Login | As a user I need to be able to log in to the system so I can access the system. | High | 4
4 | Create group | As a user I need to be able to create a group so that our sprints can be organized | High | 5
Developer
7 | Complete tasks | As a developer I need to be able to complete tasks and stories of any sprint so the data can be updated | High | 8
8 | View Group information | As a developer I need to able to view my group members and their assigned roles so I can have a complete overview of my group | High | 6
9 | View Sprint Backlog | As a developer I need to be able to see the any Sprint Backlog so I can have an overview of the current progress. | HIgh | 9
10 | View tasks | As a developer I need to be able to see the status of the current tasks so I can be aware of the progress of my team. | High | 9
11 | View Product Backlog | As a developer I need to be able to view the backlog items from Product Backlog so I can be aware of the current status of the project | High | 8
12 | Comments | As a developer I need to be able to create and remove comments on sprint backlog items to effectively communicate ideas between the group members | Low | 7
13 | Comments | As a developer I need to be able to create and remove comments on product backlog items to effectively communicate ideas between the group members | Low | 7
14 | Respond to comments | As a developer I need to be able to react to any comment to effectively communicate between group members | Low | 8
15 | Communicate with supervisor | As a developer I need to be able to communicate with the supervisor to get help if something is wrong. | Medium | 10
Manager
GROUP
16 | Add members to group | As a manager I need to be able to add and remove members from a group to keep the correct members in the group | High | 3
17 | Remove members from group | As a manager I need to be able to remove group members from a group to keep the correct members in the group | High | 3
18 | View Group information | As a manager I need to able to view my group members and their assigned roles so I can have a complete overview of my group | Medium | 6
19 | Change members roles | As a manager I need to be able to change the access of the members so that everyone has the correct authorization | High | 6
20 | Communicate with supervisor | As a manageer I need to be able to communicate with the supervisor to get help if something is wrong. | Medium | 10
PRODUCT BACKLOG
21 | Create product backlog | As a manager I need to be able to create a product backlog to store the user stories of the system | High | 2
22 | Add story to product backlog | As a manager I need to be able to add user stories to the product backlog to keep track of the current user stories | High | 4
23 | Remove story from product backlog | As a manager I need to be able to remove user stories from the product backlog to keep track of the current user stories | Medium | 6
24 | Assign story points to stories | As a manager I need to be able to assign story points to a user story to accurately depict the progress | High | 7
25 | View Product Backlog | As a manager I need to be able to view the backlog items from Product Backlog so I can be aware of the current status of the project | Medium | 8
26 | Edit Product Backlog items | As a manager I need to be able to change the Product Backlog items to keep them accurate | Low | 8
27 | Comments | As a manager I need to be able to create and remove comments on product backlog items to effectively communicate ideas between the group members | Low | 7
28 | Respond to comments | As a manager I need to be able to react to any comment to effectively communicate between group members | Low | 8
SPRINT / SPRINT BACKLOG
29 | Set sprint amount | As a manager I need to be able to set the number of sprints so that we can have an overview of the total number of sprints | High | 3
30 | View Sprint Backlog | As a manager I need to be able to see any Sprint Backlog so I can have an overview of the current progress. | Medium | 9
31 | Edit numbers of Sprint | As a manager I need to be able to edit the number of Sprints in case the initial number was a mistake. | High | 3
32 | Send user story from product backlog to sprint backlog | As a manager I need to be able to send user stories from product backlog to sprint backlog to keep the accounts accurate | High | 8
33 | Set sprint duration | As a manager I need to be able to set the duration of each sprints so that they accurately depict the time spent | High | 3
34 | Send user story from sprint backlog back to product backlog | As a manager I need to be able send user stories from sprint backlog to product backlog to keep the accounts accurate | Medium | 8
35 | Add tasks to user stories | As a manager I need to be able to add tasks to user stories to break down tasks and make them more approachable | High | 8
36 | View tasks | As a manager I need to be able to see the status of the current tasks so I can be aware of the progress of my team. | Medium | 9
37 | Complete tasks | As a manager I need to be able to complete tasks and stories of any sprint to the data can be updated | Medium | 7
38 | Comments | As a manager I need to be able to create and remove comments on sprint backlog items to effectively communicate ideas between the group members | Low | 8
MEETINGS / LOG
39 | Create log | As a manager I need to be able to create a log for the day to keep accurate documentation of the project | Low | 7
40 | Input data to log | As a manager I need to be able to input attendance and hours worked and issues of the day to the daily log to keep accurate documentation on the progress | Low | 7
41 | Create minutes of meeting | As a manager I need to be able to create meeting note to keep accurate documentation of the project | High | 10
42 | View meeting notes | As a manager I need to be able to view the meeting notes so I can have an overview on the situation | High | 8
43 | Edit meeting notes | As a manager I need to be able to edit the meetings so I can avoid human errors. | High | 8
Supervisor
44 | View sprint information | As a supervisor I need to be able to see the sprint information of any group to effectively help them. | High | 10
45 | View backlog information | As a supervisor I need to be able to see the sprint information of any group to effectively help them. | High | 10
46 | Communicate with group | As a supervisor I need to able to communicate with the group to able to announce them on the new meeting times. | High | 12
System
47 | Return stories to backlog | The system should be able to put story points back in the product backlog after a completed sprint so that no user story is left unfinished | Medium | 8
48 | Complete/not complete | The system should be able to distinguish between completed and not completed user stories to keep track of the progress on them | High | 10
49 | Calculate completed story points | The system should be able to accurately calculate completed story points to help illustrate the progress | Medium | 6
50 | Generate burndown chart | The system should be able to generate a burndown chart to help the team visualize the progress | Medium | 12
51 | Generate velocity chart | The system should be able to generate a velocity chart to help the team visualize the speed of the progress | Medium | 12
Documentation
52 | Process Report | Process Report | High
53 | Project Report | Project Report | High
54 | Security Assesment | Security Assesment | High

## Burndown chart
Day | Date | Story Points |  | Remaining |  | Done
|  | Planned | Actual | Planned | Actual | Done today
0 |  | 0 | 0 | 168 | 168
1 | 23/10/2019 | 8 | 5 | 160 | 163 | 5
2 | 30/10/2019 | 8 | 5 | 152 | 158 | 5
3 | 2019-06-11 | 8 | 3 | 144 | 155 | 3
4 | 2019-08-11 | 8 | 1 | 136 | 154 | 1
5 | 13/11/2019 | 8 | 2 | 128 | 152 | 2
6 | 20/11/2019 | 8 | 1 | 120 | 151 | 1
7 | 27/11/2019 | 8 | 5 | 112 | 150 | 5
8 | 28/11/2019 | 8 | 6 | 104 | 144 | 6
9 | 2019-02-12 | 8 | 5 | 96 | 139 | 5
10 | 2019-03-12 | 8 | 5 | 88 | 134 | 5
11 | 2019-04-12 | 8 | 9 | 80 | 125 | 9
12 | 2019-06-12 | 8 | 10 | 72 | 115 | 10
13 | 2019-09-12 | 8 | 6 | 64 | 109 | 6
14 | 2019-10-12 | 8 | 8 | 56 | 101 | 8
15 | 2019-11-12 | 8 | 9 | 48 | 92 | 9
16 | 2019-12-12 | 8 | 10 | 40 | 82 | 10
17 | 13/12/2019 | 8 | 10 | 32 | 72 | 10
18 | 16/12/2019 | 8 | 3 | 24 | 69 | 3
19 | 17/12/2019 | 8 | 10 | 16 | 59 | 10
20 | 18/12/2019 | 8 | 10 | 8 | 49 | 10
21 | 19/12/2019 | 8 | 5 | 0 | 44 | 5

## Sprint #1 Backlog
Sprint #1
Id | Product backlog items | User story | Story point | Assigned | Status
1 | Create account | As a user I need to be able to create an account so I can be added to a group. | 3 | Jaume | Not completed
2 | Login | As a user I need to be able to log in to the system so I can access the system | 4 | Jaume | Not completed
3 | Create group | As a user I need to be able to create a group so that our sprints can be organized | 5 | Florin | Not completed
4 | Add members to group | As a manager I need to be able to add and remove members from a group to keep the correct members in the group | 3 | Dave | Not completed
5 | Remove members from group | As a manager I need to be able to remove group members from a group to keep the correct members in the group | 3 | Dave | Not completed
6 | Create product backlog | As a manager I need to be able to create a product backlog to store the user stories of the system | 2 | Kenneth | Not completed
7 | Add user stories to product backlog | As a manager I need to be able to add user stories to the product backlog to keep track of the current user stories | 4 | Florin | Not completed

## Sprint #2 Backlog
Sprint #2
Id | Product backlog items | User story | Story point | Assigned | Status
1 | Create account | As a user I need to be able to create an account so I can be added to a group. | 1 | Jaume | Not completed
2 | Login | As a user I need to be able to log in to the system so I can access the system | 2 | Jaume | Not completed
3 | Create group | As a user I need to be able to create a group so that our sprints can be organized | 3 | Florin | Not completed
4 | Add members to group | As a manager I need to be able to add and remove members from a group to keep the correct members in the group | 1 | Dave | Not completed
5 | Remove members from group | As a manager I need to be able to remove group members from a group to keep the correct members in the group | 1 | Dave | Not completed
6 | Create product backlog | As a manager I need to be able to create a product backlog to store the user stories of the system | 1 | Kenneth | Not completed
7 | Add user stories to product backlog | As a manager I need to be able to add user stories to the product backlog to keep track of the current user stories | 2 | Florin | Not completed

## Sprint #3 Backlog
Sprint #3
Id | Product backlog items | User story | Story point | Assigned | Status
1 | Set number of Sprints | As a manager I need to be able to set the number of sprints so that we can have an overview of the total number of sprints | 3 | Florin | Completed
2 | Set duration of Sprints | As a manager I need to be able to set the duration of each sprints so that they accurately depict the time spent | 3 | Dave | Completed
3 | Edit number of Sprints | As a manager I need to be able to edit the number of Sprints in case the initial number was a mistake. | 3 | Jaume | Completed
4 | Create account | As a user I need to be able to create an account so I can be added to a group. | 1 | Jaume | Completed
5 | Login | As a user I need to be able to log in to the system so I can access the system | 1 | Jaume | Completed
6 | Create group | As a user I need to be able to create a group so that our sprints can be organized | 1 | Florin | Completed
7 | Add members to group | As a manager I need to be able to add and remove members from a group to keep the correct members in the group | 1 | Dave | Completed
8 | Remove members from group | As a manager I need to be able to remove group members from a group to keep the correct members in the group | 1 | Dave | Completed
9 | Create product backlog | As a manager I need to be able to create a product backlog to store the user stories of the system | 1 | Kenneth | Completed
10 | Add user stories to product backlog | As a manager I need to be able to add user stories to the product backlog to keep track of the current user stories | 1 | Florin | Completed

## Sprint #4 Backlog
Sprint #4
Id | Product backlog items | User story | Story point | Assigned | Status
1 | Send user story from product backlog to sprint backlog | As a manager I need to be able to send user stories from product backlog to sprint backlog to keep the accounts accurate | 8 | Florin | Completed
2 | Send user story from sprint backlog back to product backlog | As a manager I need to be able send user stories from sprint backlog to product backlog to keep the accounts accurate | 8 | Dave | Completed
3 | Add tasks to user story | As a manager I need to be able to add tasks to user stories to break down tasks and make them more approachable | 8 | Jaume | Completed

## Sprint #5 Backlog
Sprint #5
Id | Product backlog items | User story | Story point | Assigned | Status
1 | Change members roles | As a manager I need to be able to change the access of the members so that everyone has the correct authorization | 6 | Florin | Completed
2 | Assign story points | As a manager I need to be able to assign story points to a user story to accurately depict the progress | 7 | Dave | Completed
3 | Create minutes of meeting | As a manager I need to be able to create meeting note to keep accurate documentation of the project | 10 | Jaume | Completed

## Sprint #6 Backlog
Sprint #6
Id | Product backlog items | User story | Story point | Assigned | Status
1 | View product backlog | As a manager I need to be able to view the backlog items from Product Backlog so I can be aware of the current status of the project | 8 | Florin | Completed
2 | View sprint backlog | As a manager I need to be able to see the any Sprint Backlog so I can have an overview of the current progress. | 9 | Dave | Completed
3 | View group information | As a manager I need to able to view my group members and their assigned roles so I can have a complete overview of my group | 6 | Jaume | Completed
4 |  | Process Report |  | Florin | Not Completed
5 |  | Project Report |  | Florin | Not Completed
6 |  | Security assesment |  | Florin | Not Completed

## Sprint #7 Backlog
Sprint #7
Id | Product backlog items | User story | Story point | Assigned | Status
1 |  | Process Report |  | All | Completed
2 |  | Project Report |  | All | Completed
3 |  | Security assesment |  | All | Completed
4 | View meeting notes | As a manager I need to be able to view the meeting notes so I can have an overview on the situation | 8 | Dave | Completed
5 | View tasks | As a manager I need to be able to see the status of the current tasks so I can be aware of the progress of my team. | 9 | Jaume | Completed
6 | Edit meeting notes | As a manager I need to be able to edit the meetings so I can avoid human errors. | 8 | Florin | Completed